## Somalia DRMS and PEA
Key: Purple = Somalia and Madagascar overlap; Blue = Somalia only; Grey = optional steps | 2023-05-01 |  |  |  | 2023-06-22 |  |  |  |  | 2023-07-01 |  |  |  | 2023-08-18 |  |  |  |  | Sept-23 |  |  |  | 2023-10-18 |  |  |  | 2023-11-18 |  |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01
| 2023-01-05 | 2023-08-12 | 15-19 | 22-26 | 29-2 | 2023-05-09 | 2023-12-16 | 19-23 | 26-30 | 2023-03-07 | 2023-10-14 | 17-21 | 24-28 | 31-4 | 2023-07-11 | 14-18 | 21-25 | 28-1 | 2023-04-08 | 2023-11-15 | 18-22 | 25-29 | 2023-02-06 | 2023-09-13 | 16-20 | 23-27 | 30-3 | 2023-06-10 | 13-17 | 20-24 | 27 -1 | 2023-04-08 | 2023-11-15 | 18-22 | 25-29 | 2023-01-05 | 2023-08-12 | 15-19 | 22-26 | 29-2 | 2023-05-09 | 2023-12-16 | 19-23 | 26-1 | 2023-04-08 | 2023-11-15 | 18-22 | 25-29 | 2023-01-05 | 2023-08-12 | 15-19 | 22-26 | 29-3
Call for Concept Notes
Selection of Team |  |  |  |  | 31
Issuance of mod and completion of sub-awardees agreements | [5 empty] | 9
Co-Creation of Program Description | [6 empty] | 16
Workplan Submission to USAID and LASER | [7 empty] | 23
Work Plan Review by USAID and LASER | [8 empty] | 30
Data Collection Tool Creation | [10 empty] | 14
Data Collection Tool Submission to USAID and LASER | [10 empty] | 14
Data Collection Tool Review by USAID and LASER | [11 empty] | 21
IRB Preparation
IRB Submission and Approval | [14 empty] | 11 |  |  |  |  | 15
Report Outline Creation | [15 empty] | 18
Report Outline Submission to USAID | [15 empty] | 18
Report Outline Review by USAID and LASER | [16 empty] | 22
Secondary Data Collection and Analysis
Annotated Bibliography Creation
Annotated Bibliography Submission to LASER for Review | [19 empty] | 15
Annotated Bibliography Review by LASER | [20 empty] | 20
Annotated Bibliography Revisions | [20 empty] | 22
Annotated Bibliography Review by USAID | [21 empty] | 27
Data Collection Preparations (incl 2 weeks after IRB prep for logistics)
Primary Data Collection
Data Analysis
Presentation of Initial Findings and Feedback to Researchers
Report Writing
Reports due to LASER for RPM Review | [30 empty] | 1
Report revision based on RPM revision and submission to OU for Review | [31 empty] | 8
Report Revision based on OU Review | [32 empty] | 15
Reports due to LASER for RPWG Review (optional to confirm quality) | [33 empty] | 22
Report Revision (optional if necessary) | [34 empty] | 29
FINAL reports sent to USAID for review | [35 empty] | 5
USAID review | [36 empty] | 12
508 compliance | [37 empty] | 18
Final Submission of Reports for Publication | [37 empty] | 19

## Madagascar Timeline for Applica
Study/Project | Deliverables and Key Milestones | 2023-06-22 |  |  |  |  | 2023-07-01 |  |  |  | 2023-08-18 |  |  |  |  | Sept-23 |  |  |  | 2023-10-18 |  |  |  | 2023-11-18 |  |  |  |  | 2023-12-01
|  | 29-2 | 2023-05-09 | 2023-12-16 | 19-23 | 26-30 | 2023-03-07 | 2023-10-14 | 17-21 | 24-28 | 31-4 | 2023-07-11 | 14-18 | 21-25 | 28-1 | 2023-04-08 | 2023-11-15 | 18-22 | 25-29 | 2023-02-06 | 2023-09-13 | 16-20 | 23-27 | 30-3 | 2023-06-10 | 13-17 | 20-24 | 27 -1 | 2023-04-08 | 2023-11-15 | 18-22 | 25-29
DRMS & PEA | Announcement of the Selected Team | 31
| Issuance of mod and completion of sub-awardees agreements | 2
| Co-Creation of Program Description |  | 9
| Workplan Submission to USAID |  |  | 16
| Work Plan Review (by LASER and USAID) |  |  |  | 20
Data Collection Tool Creation
| Data Collection Tool Submission to USAID and LASER |  |  |  | 20
| Data Collection Tool Review (by LASER and USAID) |  |  |  | 23
| IRB Preparation |  |  |  |  | 30
| IRB Submission and Approval | [5 empty] | 3 |  |  | 28
Report Outline Creation
| Report Outline Submission (to LASER and USAID) | [5 empty] | 7
| Report Outline Review (by LASER and USAID) | [6 empty] | 12
Secondary Data Collection and Analysis
Annotated Bibliography Creation
| Annotated Bibliography Submission to LASER for Review | [8 empty] | 28
| Annotated Bibliography Review by LASER | [9 empty] | 4
| Annotated Bibliography Revisions | [10 empty] | 9
| Annotated Bibliography Review by USAID | [10 empty] | 11
Data Collection Preparations (incl 2 weeks after IRB prep for logistics)
Primary Data Collection
Data Analysis
| Presentation of Initial Findings and Feedback to Researchers | [18 empty] | 6
Report Writing
| Reports due to LASER for RPM Review | [21 empty] | 27
| Report revision based on RPM revision and submission to OU for Review | [23 empty] | 10
| Report Revision based on OU Review | [25 empty] | 24
| Reports due to LASER for RPWG Review | [27 empty] | 8
Report Revision based on RPWG Review
| FINAL reports sent to USAID for review | [29 empty] | 22
| USAID review | [30 empty] | 28
| 508 compliance | [30 empty] | 29
| Final Submission of Reports for Publication | [30 empty] | 29
SDA | Co-creation of program description and submission, review and revision, and final submission and approval
Workplan co-creation and submission, review and revision, and final submission and approval
Background literature review creation and submission, review and revision, and final submission and approval
Data acquisition from DHS, data management, data cleaning, and data exploration
Data analysis plan creation and submission, review and revision, and final submission and approval
Carry out descriptive and inferential statistical analysis, and econometrics analysis
Presenting initial findings using powerpoint slides and data visualization, presentation feedback and discussion on next steps
Preparing and submitting the final report outline, review and revision, and final submission and approval
| SDA report creation and submission to LASER for review and feedback | [14 empty] | 8
| LASER review of the SDA report and submission of feedback to the research team | [15 empty] | 15
| SDA report revision by research team and submission to USAID for review and feedback | [16 empty] | 22
| USAID review of the SDA report and submission of feedback (First Round) | [17 empty] | 29
| SDA report revision and submission by research team to USAID for review and feedback | [19 empty] | 13
| USAID review of the SDA report and submission of feedback (Second Round) | [20 empty] | 20
| Final SDA report revision and submission by research team to LASER and USAID for review and approval | [21 empty] | 7
| SDA dataset and metadata preparation and submission for review, revision, and final submission and approval | [18 empty] | 6
| SDA dataset and metadata review by LASER and USAID, and feedback | [19 empty] | 13
| Final SDA dataset and metadata revision and submission by research team to LASER and USAID | [20 empty] | 20
| Final SDA report remediation for 505 compliance and upload on DEC, and SDA metadata upload on DDL | [22 empty] | 3

## Jess temp Copy of Madagascar SD (hidden)
Key: Purple = Somalia and Madagascar overlap; Blue = Madagascar only; Grey = optional steps | 2023-05-01 |  |  |  | 2023-06-22 |  |  |  |  | 2023-07-01 |  |  |  | 2023-08-18 |  |  |  |  | Sept-23 |  |  |  | 2023-10-18 |  |  |  | 2023-11-18 |  |  |  |  | 2023-12-01 |  |  |  | 2024-01-01 |  |  |  |  | 2024-02-01 |  |  |  | 2024-03-01 |  |  |  | 2024-04-01
| 2023-01-05 | 2023-08-12 | 15-19 | 22-26 | 29-2 | 2023-05-09 | 2023-12-16 | 19-23 | 26-30 | 2023-03-07 | 2023-10-14 | 17-21 | 24-28 | 31-4 | 2023-07-11 | 14-18 | 21-25 | 28-1 | 2023-04-08 | 2023-11-15 | 18-22 | 25-29 | 2023-02-06 | 2023-09-13 | 16-20 | 23-27 | 30-3 | 2023-06-10 | 13-17 | 20-24 | 27 -1 | 2023-04-08 | 2023-11-15 | 18-22 | 25-29 | 2023-01-05 | 2023-08-12 | 15-19 | 22-26 | 29-2 | 2023-05-09 | 2023-12-16 | 19-23 | 26-1 | 2023-04-08 | 2023-11-15 | 18-22 | 25-29 | 2023-01-05 | 2023-08-12 | 15-19 | 22-26 | 29-3
Call for Concept Notes (3 weeks)
Selection of Team (1.5 weeks) |  |  |  |  | 31
Issuance of mod and completion of sub-awardees agreements
Co-Creation of Program Description (1 week) | [5 empty] | 9
Workplan Submission | [6 empty] | 16
Work Plan Review | [7 empty] | 20
Background Literature Review Creation
Background Literature Review Submission | [10 empty] | 14
Background Literature Review Review (by LASER and USAID) | [11 empty] | 19
Data Cleaning and Analysis Plan Creation
Data Cleaning and Analysis Plan Submission | [10 empty] | 14
Data Cleaning and Analysis Plan Review | [11 empty] | 19
Data Cleaning and Analysis
Initial Findings Presentation and Feedback to Researchers | [15 empty] | 14
Data Analysis Report Creation | [17 empty] | 1
Data Analysis Report Submission to LASER | [18 empty] | 8
Data Analysis Report Review by LASER | [19 empty] | 15
Data Analysis Report Revisions | [20 empty] | 22
Reports due to LASER for Review (optional to confirm quality) | [21 empty] | 29
Report Revision (optional if necessary) | [22 empty] | 6
When is data analysis report sent from LASER to USAID? | [13 empty] | ?
FINAL Data Analysis Report Review by USAID | [23 empty] | 13
USAID review | [24 empty] | 20
Tableau database/data visualization product creation
Tableau database/data visualization product submission | [19 empty] | 15
Tableau database/data visualization product review (by LASER and USAID) | [20 empty] | 22
Final, cleaned data file(s), in English, and coding language creation
Final, cleaned data file(s), in English, and coding language submission | [23 empty] | 13
Final, cleaned data file(s), in English, and coding language review (by LASER and USAID) | [25 empty] | 27
508 compliance | [26 empty] | 2
Final Submission of Deliverables for Publication | [26 empty] | 3